## Iter1
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
User Login Screen | Login page can not access google account | 1 |  | Closed | TrangVT |  | 2023-01-30 | Iter1 | Task, 3_Done | User Login
Write SRS for User Login screen | Write detailed functional specification for the User Login screen | 2 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | User Login
Write SDS for User Login screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the User Login screen | 3 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | User Login
Test for User Login screen | Code & Unit test for the User Login screen | 4 |  | Closed | VuVT |  | 2023-02-02 | Iter1 | Task, 3_Done | User Login
User Signup screen | Can not create account after click submit button | 5 |  | Closed | TrangVT |  | 2023-01-30 | Iter1 | Task, 3_Done | User Signup
Write SRS for User Signup screen | Write detailed functional specification for the User Signup screen | 6 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | User Signup
Write SDS for User Signup screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the User Signup screen | 7 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | User Signup
Test for User Signup screen | Code & Unit test for the User Signup screen | 8 |  | Closed | TrangVT |  | 2023-02-02 | Iter1 | Task, 3_Done | User Signup
Homepage Screen | The product shown is not the correct size in row | 9 |  | Closed | VuVT |  | 1/30/2023 | Iter1 | Task, 3_Done | Homepage
Write SRS for Homepage Screen | Write detailed functional specification for the Homepage Screen | 10 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | Homepage
Write SDS for Homepage Screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Homepage Screen | 11 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | Homepage
Test for User Homepage Screen | Code & Unit test for the Homepage Screen | 12 |  | Closed | VuVT |  | 2023-02-02 | Iter1 | Task, 3_Done | Homepage
Product Page | All Product Page cannot display any products | 13 |  | Closed | VuVT |  |  | Iter1 | Task, 3_Done | Product page
Write SRS for Product Page | Write detailed functional specification for the Product Page | 14 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | Product page
Write SDS for Product Page | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Product Page | 15 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | Product page
Test for Product Page | Code & Unit test for the Product Page | 16 |  | Closed | VuVT |  | 2023-02-02 | Iter1 | Task, 3_Done | Product page
User Profile | avatar image from account can not display | 17 |  | Closed | Huy |  |  | Iter1 | Task, 3_Done | User Profile
Validate Edit Profile | have not validated the data entered | 18 |  | Closed | Huy |  |  | Iter1 | Task, 3_Done | User Profile
Write SRS for User Profile | Write detailed functional specification for the User Profile | 19 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | User Profile
Write SDS for User Profile | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the User Profile | 20 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | User Profile
Test for User Profile | Code & Unit test for the User Profile | 21 |  | Closed | Huy |  | 2023-02-02 | Iter1 | Task, 3_Done | User Profile
Coding | Some members have difficulty in coding and updating code | 22 |  | Closed | All member |  | 2023-11-03 | Iter1 | Task, 3_Done | User Login
Admin Dashboard Screen | Can not get data from admin role | 23 |  | Closed | Thanh |  | 1/30/2023 | Iter1 | Task, 3_Done | Admin Dashboard Screen
Write SRS for Admin Dashboard Screen | Write detailed functional specification for the Admin Dashboard Screen | 24 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | Admin Dashboard Screen
Write SDS for Admin Dashboard Screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Admin Dashboard Screen | 25 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | Admin Dashboard Screen
Test for Admin Dashboard Screen | Code & Unit test for the Admin Dashboard Screen | 26 |  | Closed | Thanh |  | 2023-02-02 | Iter1 | Task, 3_Done | Admin Dashboard Screen
Employee Management | Can not create employee | 27 |  | Closed | Quyen |  | 1/30/2023 | Iter1 | Task, 3_Done | Employee Management
Write SRS for Employee Management | Write detailed functional specification for the Employee Management | 28 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | Employee Management
Write SDS for Employee Management | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Employee Management | 29 |  | Closed | all member |  | 2023-01-02 | Iter1 | Task, 3_Done | Employee Management
Test for Employee Management | Code & Unit test for the Employee Management | 30 |  | Closed | VuVT |  | 2023-02-02 | Iter1 | Task, 3_Done | Employee Management
Github | Some members have difficulty to use github | 31 |  | Closed | all team |  |  | Iter1

## Iter2
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Write SRS for Product Detail screen | Write detailed functional specification for the Product Detail screen | 1 |  | Closed | all member |  | 2023-02-08 | Iter2 | Task, 3_Done | Product Detail
Write SDS for Product Detail screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Product Detail screen | 2 |  | Closed | all member |  | 2023-02-08 | Iter2 | Task, 3_Done | Product Detail
Test for Product Detail screen | Code & Unit test for the Product Detail screen | 3 |  | Closed | VuVT |  | 2023-02-08 | Iter2 | Task, 3_Done | Product Detail
Cart | Can not count products in cart | 4 |  | Closed | VuVT |  | 2023-02-11 | Iter2 | Task, 3_Done | Cart
Write SRS for Cart screen | Write detailed functional specification for the Cart screen | 5 |  | Closed | all member |  | 2023-02-11 | Iter2 | Task, 3_Done | Cart
Write SDS for Cart screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Cart screen | 6 |  | Closed | all member |  | 2023-02-11 | Iter2 | Task, 3_Done | Cart
Test for Cart screen | Code & Unit test for the Cart screen | 7 |  | Closed | VuVT |  | 2023-02-11 | Iter2 | Task, 3_Done | Cart
Write SRS for Add To Cart | Write detailed functional specification for the Add To Cart Function | 8 |  | Closed | all member |  | 2023-02-13 | Iter2 | Task, 3_Done | Cart
Write SDS for Add To Cart Screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Add To Cart Function | 9 |  | Closed | all member |  | 2023-02-13 | Iter2 | Task, 3_Done | Cart
Test for Add To Cart Function | Code & Unit test for the Add To Cart Function | 10 |  | Closed | TrangVT |  | 2023-02-13 | Iter2 | Task, 3_Done | Cart
Write SRS for Manage Orders Screen | Write detailed functional specification for the Manage Orders Screen | 11 |  | Closed | all member |  | 2023-02-13 | Iter2 | Task, 3_Done | Manage Orders Screen
Write SDS for Manage Orders Screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Manage Orders Screen | 12 |  | Closed | all member |  | 2023-02-13 | Iter2 | Task, 3_Done | Manage Orders Screen
Write SRS for Employees Management | Write detailed functional specification for the Employees Management | 13 |  | Closed | all member |  | 2023-02-13 | Iter2 | Task, 3_Done | Employees Management
Write SDS for Employees Management | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Employees Management | 14 |  | Closed | all member |  | 2023-02-13 | Iter2 | Task, 3_Done | Employees Management
Coding | Some members have to learn more to code the function | 15 |  | Closed | All member |  | 2023-02-13 | Iter2 | Task, 3_Done
Github | Conflict project on github | 16 |  | Closed | all team |  |  | Iter2

## Iter3
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
FeedBack Screen | Can not upload image | 1 |  | Closed | VuVT |  | 2023-02-26 | Iter3 | Task, 3_Done | Feedback
Write SRS for FeedBack screen | Write detailed functional specification for the FeedBack screen | 2 |  | Closed | all member |  | 2023-02-26 | Iter3 | Task, 3_Done | Feedback
Write SDS for FeedBack screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the FeedBack screen | 3 |  | Closed | all member |  | 2023-02-26 | Iter3 | Task, 3_Done | Feedback
Test for FeedBack screen | Code & Unit test for the FeedBack screen | 4 |  | Closed | VuVT |  | 2023-02-26 | Iter3 | Task, 3_Done | Feedback
Write SRS for Voucher Management screen | Write detailed functional specification for the User Signup screen | 5 |  | Closed | all member |  | 2023-02-26 | Iter3 | Task, 3_Done | Voucher Management
Write SDS for Voucher Management screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Voucher Management screen | 6 |  | Closed | all member |  | 2023-02-26 | Iter3 | Task, 3_Done | Voucher Management
Test for Products Catalogue | Code & Unit test for the Products Catalogue | 7 |  | Closed | TrangVT |  | 2023-03-03 | Iter3 | Task, 3_Done | Homepage
Write SRS for Search Products Screen | Write detailed functional specification for the Homepage Screen | 8 |  | Closed | all member |  | 2023-03-03 | Iter3 | Task, 3_Done | Homepage
Write SDS for Search Products Screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Homepage Screen | 9 |  | Closed | all member |  | 2023-03-03 | Iter3 | Task, 3_Done | Homepage
Rating Products | Rating stars do not display right | 10 |  | Closed | VuVT |  | 2023-03-03 | Iter3 | Task, 3_Done | Product page
Write SRS for Rating Products | Write detailed functional specification for the Rating Products | 11 |  | Closed | all member |  | 2023-03-03 | Iter3 | Task, 3_Done | Product page
Write SDS for Rating Products | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the Rating Products | 12 |  | Closed | all member |  | 2023-03-03 | Iter3 | Task, 3_Done | Product page
Test for Rating Products | Code & Unit test for the Rating Products | 13 |  | Closed | VuVT |  | 2023-03-03 | Iter3 | Task, 3_Done | Product page
Order Status | can't show pagination after showing order by status | 14 |  | Closed | TrangVT |  | 2023-03-03 | Iter3 | Task, 3_Done | Order Management
Filter for product | can't show pagination after showing product by status | 15 |  | Closed | TrangVT |  | 2023-03-03 | Iter3 | Task, 3_Done | Product Management

## Ite4
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Finish SRS Documents | Write detailed functional specification for all project | 1 |  | Open | all member |  | 3/21/2023 | Iter4 | Task, 2_Doing
Finish SDS Documents | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the all project | 2 |  | Open | all member |  | 3/21/2023 | Iter4 | Task, 2_Doing
Finish Project Tracking | Write all of finallize function of project | 3 |  | Open | all member |  | 3/21/2023 | Iter4 | Task, 2_Doing
Write Final Release Document | Write detailed instructions for Final Release Document | 4 |  | Open | all member |  | 3/21/2023 | Iter4 | Task, 2_Doing
Finish Product Backlog | Finish the Product Backlog Documents | 5 |  | Open | all member |  | 3/21/2023 | Iter4 | Task, 2_Doing
Write SRS for Search Products Screen | Write detailed functional specification for the Homepage Screen | 6 |  | Open | all member |  | 3/21/2023 | Iter4 | Task, 2_Doing
Commit all codes of project | Commit all codes to team's github project | 7 |  | Open | all member |  | 3/21/2023 | Iter4 | Task, 2_Doing