## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home Page | Public | Show slider, Show hot selling products, New products, product search toolbar -Slider information: image, title; the user is redirected to the slider's backlink on his/her clicking -Product information: photo, title, price, book information: author, genre, book introduction, publication date, quantity | VuVT | Done | Done | Done
2 | Voucher Management | Private | This screen displays the list of vouchers being applied in the system and in the store, the types of vouchers, the discount price of the voucher and the time of using the voucher. There are functions in the screen: delete voucher, edit voucher, update voucher | HuyNQ | Done | Done | Done
3 | Store Management | Private | This screen will display the functional items in Store Management, to display the items in the store and admin will easily manage the parts in the store. | HuyNQ | Done | Done | Done
4 | Employees Management | Private | This screen displays a list of employees working in the store, displaying information including:Employee ID, Name,Gender,Department Name,Title,TitleOfCoursity,Birthday, HireDate, Adress, phone number, status. In the interface there are functions filter, search, create new employee, change order status | ThanhDC | Done | Done | Done
5 | User Login,User Register | Common | Is the screen that displays the interface for users to log in, in the user interface can log in with facebook or google via the link, there are links in this interface to register or retrieve the password. | TrangVT | Done | Done | Done

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Profile Management | Common | This screen displays the user's information including: photo, account or login link, name, address, birthday, phone number,gender, contact title, create date. Besides, there are additional functions in the screen: All Order (see all orders), Edit profile | HuyNQ | Done | Done | Done
2 | Manage Orders | Common | This screen shows the orders that the user has purchased, the order in the cart and displays information about the product: OrderID,Order date,Status,Total paid | ThanhDC | Done | Done | Done
6 | DashBoard | Private | This screen lists out the total revenue, number of products, number of new employees for the selected period, there is a bar chart to track the web's up and down trends | HuyNQ | Done | iter2 | iter3
4 | View Product | Private | This screen displays the products in stock, displaying the product's attributes: Product ID, Product Name, Category Name, Genre Name, Cover Price, Sale Price,Author Name,Translator,Punlisher Name, Supplie Displays Filter, Search, Create a new Product buttons | QuyenKTH | Done | Done | Done
5 | Edit Product | Private | This screen displays the information boxes that the admin wants to change: Product ID, Product Name, Category Name, Genre Name, Cover Price, Sale Price, Author Name,Translator,Punlisher Name, Supplie,Language,Book Size, Book weight ,Number of pages,Format,Image Click the save button to return to the Products view page | QuyenKTH | Done | Done | Done
6 | Update Profile | Common | This screen shows information that users can optionally edit personal information: name, address, birthday, phone number, gen, contact title, create date | HuyNQ | Done | Done | Done

## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Home Page | Public | Anyone | Show slider, Show hot selling products, New products, product search toolbar -Slider information: image, title; the user is redirected to the slider's backlink on his/her clicking -Product information: photo, title, price, book information: author, genre, book introduction, publication date, quantity | VuVT | Done | iter1 | iter2
2 | User Login,User Register | Common | User | Is the screen that displays the interface for users to log in, in the user interface can log in with facebook or google via the link, there are links in this interface to register or retrieve the password. | TrangVT | Done | iter2 | iter3
3 | Profile Management | Common | Customer | This screen displays the user's information including: photo, account or login link, name, address, birthday, phone number,gender, contact title, create date. Besides, there are additional functions in the screen: All Order (see all orders), Edit profile | HuyNQ | Done | iter2 | iter3
4 | Update Profile | Common | Customer | This screen shows information that users can optionally edit personal information: name, address, birthday, phone number, gen, contact title, create date | HuyNQ | Done | iter2 | iter3
5 | Manage Orders | Common | Customer | This screen shows the orders that the user has purchased, the order in the cart and displays information about the product: OrderID,Order date,Status,Total paid | ThanhDC | Done | iter2 | iter3
6 | DashBoard | Private | Admin | This screen lists out the total revenue, number of products, number of new employees for the selected period, there is a bar chart to track the web's up and down trends | HuyNQ | Done | iter2 | iter3
7 | View Product | Private | Admin | This screen displays the products in stock, displaying the product's attributes: Product ID, Product Name, Category Name, Genre Name, Cover Price, Sale Price,Author Name,Translator,Punlisher Name, Supplie Displays Filter, Search, Create a new Product buttons | QuyenKTH | Done | iter2 | iter3
8 | Edit Product | Private | Admin | This screen displays the information boxes that the admin wants to change: Product ID, Product Name, Category Name, Genre Name, Cover Price, Sale Price, Author Name,Translator,Punlisher Name, Supplie,Language,Book Size, Book weight ,Number of pages,Format,Image Click the save button to return to the Products view page | QuyenKTH | Done | iter2 | iter4
9 | View Order | Private | Admin | The screen displays all the orders in the data, the orders placed by the buyer and it displays the order information: OrderID,Customer Name, Employee Name,Order date,Required date,Shipped date,Ship Address,Ship City ,Status -There are buttons to push Filter, Search, Change Order status | ThanhDC | Done | iter3 | iter4
10 | Filter Order | Private | Admin | -After the admin clicks "Filter" the screen will display the Orders that are filtered according to the Admin's request -Admin selects by Order Date to display orders in the time period that the admin wants | ThanhDC | Done | iter3 | iter4
11 | Change Order Status | Private | Admin | On the screen of the order list shows the status of status, beside each initial status of the statusm, Admin can change the states depending on the initial status of the Order After pressing change, a message will appear: +click "ok" to return to the order list screen and change the status of the order +click "cancle" to return to the order list screen and keep the original state of the order | ThanhDC | Done | iter3 | iter4
12 | My Cart | Common | Customer/Guest | This screen displays the products that Customer/Guest added to his cart,In this picture shows the book's title, the number of books purchased (with a button to change the quantity of the book), Price. The right corner shows the total price of the book in the buyer's cart | VuVT | Done | iter3 | iter4
13 | FeedBack | Common | Customer | in this screen shows the Orders that the buyer has placed, including book ID, Orderdate, status. In each section of the order, there is a product review section, buyers can rate by rating, comment and submit their review of the product by pressing the "Review" button. | VuVT | Done | iter3 | iter4
14 | Products Catalogue | Common | Customer/Guest | This screen displays options Allow users to search for products by interest, use product classification criteria to filter the list of products they want to buy -Users can search by title in the screen, and select options to filter by request, category, and price that the user wants. | TrangVT | Done | iter3 | iter4
15 | Employees Management | Private | Admin | This screen displays a list of employees working in the store, displaying information including:Employee ID, Name,Gender,Department Name,Title,TitleOfCoursity,Birthday, HireDate, Adress, phone number, status. In the interface there are functions filter, search, create new employee, change order status | ThanhDC | Done | iter3 | iter4
16 | Create new Employee | Private | Admin | in this screen display information about employees for admin to provide data and add to the list of employees in the store. Admin will have to provide full information about the new employee: Name,Title,Status,Birth date, Phone number,Gender,TitleOfCoursity,Address,Department | ThanhDC | Done | iter3 | iter4
17 | Store Management | Private | Admin | This screen will display the functional items in Store Management, to display the items in the store and admin will easily manage the parts in the store. | HuyNQ |  | iter3 | iter4
18 | Voucher Management | Private | Admin | This screen displays the list of vouchers being applied in the system and in the store, the types of vouchers, the discount price of the voucher and the time of using the voucher. There are functions in the screen: delete voucher, edit voucher, update voucher | HuyNQ |  | iter3 | iter4
19 | Add To Cart | Common | Customer/Admin/Employee | This screen displays the ordered products, displays information about the product, the quantity of the product, the price of the product in the cart. Update Change quantity | VuVT |  | iter4 | none
20 | Search Products | Common | Customer/Admin/Employee | This screen displays the products that Guest, Customer, Employee, Admin use to display all the products that are searched. Searching by product name or product name will show all products with the same name | VuVT |  | iter4 | none
21 | Rating Products | Common | Customer/Admin/Employee | This screen displays the rating items including: comments, ratings of the products in the store and displayed at the end of each product. To show the level and satisfaction of the person who has purchased the product | VuVT |  | iter4 | none

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | View Order | Private | The screen displays all the orders in the data, the orders placed by the buyer and it displays the order information: OrderID,Customer Name, Employee Name,Order date,Required date,Shipped date,Ship Address,Ship City ,Status -There are buttons to push Filter, Search, Change Order status | Tuấn Hà | Done | II.3 | III.5
| Filter Order | Private | -After the admin clicks "Filter" the screen will display the Orders that are filtered according to the Admin's request -Admin selects by Order Date to display orders in the time period that the admin wants
| Change Order Status | Private | On the screen of the order list shows the status of status, beside each initial status of the statusm, Admin can change the states depending on the initial status of the Order After pressing change, a message will appear: +click "ok" to return to the order list screen and change the status of the order +click "cancle" to return to the order list screen and keep the original state of the order
| My Cart | Common | This screen displays the products that Customer/Guest added to his cart,In this picture shows the book's title, the number of books purchased (with a button to change the quantity of the book), Price. The right corner shows the total price of the book in the buyer's cart
| FeedBack | Common | in this screen shows the Orders that the buyer has placed, including book ID, Orderdate, status. In each section of the order, there is a product review section, buyers can rate by rating, comment and submit their review of the product by pressing the "Review" button.
| Products Catalogue | Common | This screen displays options Allow users to search for products by interest, use product classification criteria to filter the list of products they want to buy -Users can search by title in the screen, and select options to filter by request, category, and price that the user wants.
| Create new Employee | Private | in this screen display information about employees for admin to provide data and add to the list of employees in the store. Admin will have to provide full information about the new employee: Name,Title,Status,Birth date, Phone number,Gender,TitleOfCoursity,Address,Department

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Add To Cart | Common | This screen displays the ordered products, displays information about the product, the quantity of the product, the price of the product in the cart. Update Change quantity | VuVT | Done | Done | Done
2 | Search Products | Common | This screen displays the products that Guest, Customer, Employee, Admin use to display all the products that are searched. Searching by product name or product name will show all products with the same name | VuVT | Done | Done | Done
3 | Rating Products | Common | This screen displays the rating items including: comments, ratings of the products in the store and displayed at the end of each product. To show the level and satisfaction of the person who has purchased the product | VuVT | Done | Done | Done